GloBE-Reg Clinical Study Protocol

|  |  | Page |
| --- | --- | --- |
| 1 | Administrative Information | 2 |
| 2 | Background and Rationale | 2 |
| 3 | Study Objectives | 2 |
| 4 | Study Design | 2 |
| 5 | Study Population | 2 |
| 6 | Data Collection and Study Procedures | 3 |
| 7 | Outcome Measures | 3 |
| 8 | Data Management and Quality Assurance | 3 |
| 9 | Ethical Considerations | 3 |
| 10 | Project Management and Governance | 3 |
| 11 | Stakeholder Engagement | 4 |
| 12 | Data Ownership | 4 |
| 13 | Access Procedures | 4 |
| 14 | Timeline and Milestones | 4 |
| 15 | Risk Management | 4 |
| 16 | References | 4 |
| Appendix 1 | Ethics Approval |  |
| Appendix 2 | Conditions of Ethics Approval |  |
| Appendix 3 | UK NHS Research Ethics Committee (REC) Application |  |
| Appendix 4 | Ethics Amendments |  |
| Appendix 5 | Data Protection Approval Letter |  |
| Appendix 6 | Data Dictionary |  |
| Appendix 7 | Data Flow in the Registry |  |
| Appendix 8 | Data Sharing Agreement – Data Disclosers (for centres adding data into the registry) |  |
| Appendix 9 | Participant Information Sheets (English) – Adult, Parent, Child (word versions available) |  |
| Appendix 10 | Informed Consent Form (word version) |  |
| Appendix 11 | Privacy Notices |  |

Created Date: 051125

Review Date: 051126

- Administrative Information

Full Title: Global Registry for Novel Therapies in Rare Bone & Endocrine Conditions

Short Title: GloBE-Reg

Version Date: November 2025

Principal Investigator: Professor S. Faisal Ahmed

Lead Institution: Office for Rare Conditions (ORC) Registries, University of Glasgow
Collaborating Institutions: Expert Centres (list available from ORC Registries)
Study Type: Non-interventional, retrospective and prospective, multinational registry study

- Background and Rationale

Patient registries collect uniform data to identify outcomes for populations with specific conditions or therapies. Existing endocrine registries focus mainly on natural history data and are often not designed for long-term post-authorisation safety and effectiveness monitoring of novel medicinal products. Industry-specific registries tend to be limited in scope and duration. In paediatric endocrinology, where follow-up may span several decades, registries developed in partnership between academia, industry, healthcare professionals, and patients are essential for meaningful long-term evaluation. GloBE-Reg aims to create a sustainable, global platform to support post-regulatory approval studies of novel endocrine therapies, initially focusing on recombinant human growth hormone (rhGH) as a model therapy.

- Study Objectives

Primary Objective

To establish and maintain a global registry capable of supporting post-regulatory approval studies for novel endocrine therapies, starting with rhGH.

Secondary Objectives

• To develop a sustainable and quality-assured registry infrastructure.
• To establish a multi-stakeholder governance and data-sharing framework.
• To facilitate high-quality scientific outputs and data utilisation across partners.

- To explore the incorporation of other novel therapies

- Study Design

This is a non-interventional, mixed retrospective and prospective, multinational registry study designed to collect and monitor data on patients who are eligible to receive a novel therapy for which GloBE-Reg is equipped to collect information; currently this only exists for rhGH. The registry will include a centralised electronic data capture system with a core dataset and diagnosis and therapy-specific modules. The GloBE-Reg platform will enable the collection of clinician- and patient-reported outcomes and adverse events, with translation and localisation features to ensure global accessibility.

- Study Population

Inclusion Criteria:

- Patients who are receiving a novel therapy that is included on GloBE-Reg

- Patients with a clinical condition that is a recognized indication for a novel therapy that is included on GloBE-Reg

- Consent provided by patients or guardians, as appropriate.

Exclusion Criteria:
• Patients who are not receiving a novel therapy that is included on GloBE-Reg

- Patients with a clinical condition that is not a recognized indication for a novel therapy that is included on GloBE-Reg

• Inability or unwillingness to provide informed consent.

- Data Collection and Study Procedures

The GloBE-Reg platform will collect data through four-five structured questionnaires: diagnosis, therapy, adverse events, clinician-reported outcomes, and patient/parent-reported outcomes. Data quality will be ensured through minimization of datasets, minimal use of free text, standardization of responses, automated validation, internal logic checks and external data verification and education and training of reporters. Optional remote source data verification and quality assurance exercises targeting at least 10% of entered cases per centre will also be available if required by investigators.  Data access will be governed by the Data Access Committee (DAC) following established procedures that have been established in other successful registry initiatives launched by the lead institution. The DAC ensures ethical and transparent data sharing practices. Its remit includes reviewing applications for data access, ensuring compliance with ethics approvals, and maintaining data custodianship standards. The DAC provides independent scientific advice, evaluates project overlap, and guides on dissemination and publication practices. The DAC reports to the Steering Committee through its Chair.

- Outcome Measures

Primary Outcome:
• Establishment and operation of a functional registry platform for rhGH therapies.

Secondary Outcomes:
• Development and validation of the GH-specific module
• Data completeness and accuracy metrics
• Scientific publications and dissemination outputs

- Data Management and Quality Assurance

Data will be managed centrally by the Office for Rare Conditions Registries at the University of Glasgow. The project operates under a comprehensive Data Access Policy (DAP) that governs all aspects of data handling, use, and protection. Data quality will be checked by several methods and quality assurance will be conducted using remote review meetings. Data security will comply with GDPR and institutional policies. When required, complex analyses will be performed internally or under the supervision of external investigators. Depending on the requirements of the investigators, raw data will also be shared with investigators but in this case all identifiable data shall be removed. All data sharing and scientific analysis will be regulated through formal Data Sharing Agreements that will adhere to the purpose of data sharing and as described in the data access request that was approved by the DAC. Annual analyses will also be performed by the PMG to evaluate data accrual, quality, and content, generating progress reports for the Steering Committee. All results will be disseminated transparently, with due acknowledgment of the GloBE-Reg contributors and infrastructure.

- Ethical Considerations

Ethical approval has been obtained through the University of Glasgow Research Ethics Committee and partner institutions will be expected to obtain their local centre approvals before starting to enter patient data. Opt-in or opt-out consent will be obtained prior to inclusion. The registry will adhere to the principles of confidentiality, transparency, and patient engagement. Patient representatives will be active members of the Scientific Study Group and governance committees.

- Project Management and Governance

The GloBE-Reg Project Management Group (PMG) will coordinate daily operations and report to the Steering Committee. Short-life Expert Working Groups (formerly referred to as Scientific Study Group) will oversee the development of condition or therapy-specific modules and explore the development of studies. The EWGs will cease to exist after a study has been developed. The Data Access Committee (DAC) will evaluate data requests for these studies and monitor the progress of the studies. Representation in the PMG, EWG and DAC will include academic, clinical, patient and industry stakeholders. All activities of the project are also reviewed by the University of Glasgow’s Data Protection Team and the Legal and Contracts team. This multi-tiered governance framework ensures that all registry activities adhere to ethical, legal, and scientific standards. The project will also have a Grants Review Panel, which will oversee the awarding of small grants to centres for assisting with data collection and reporting, and a Patient Advisory Group.

- Stakeholder Engagement

Stakeholders include patients, clinicians, professional societies, and industry partners. Patient organisations such as SOD Italia and ICOSEP are involved in the project Professional collaboration is established with several major endocrine societies including APPES, ANZSPED, ESPE, ESE, and GH Research Society. The project engages with the public through its website and social media presence.

- Data Ownership

Data ownership is distributed across several stakeholders:

• Patients (and/or guardians) are the primary owners of their individual data, granting non-exclusive research licences to the University of Glasgow and authorised investigators through the consent process. They can request deletion of their own data.

• The University of Glasgow owns the database infrastructure.

• The reporter’s institution owns the aggregated clinical data for their patients and can request deletion and can also download all the data themselves.

- Once supplied to the investigator and processed, the data become research data, constituting the intellectual property of the investigator.

- The University of Glasgow, through the Office for Rare Conditions Registries, serves as the custodian of the data and is responsible for its security, ethical use, and long-term storage.

- Access Procedures

Access to registry data follows a formal process:

1. Investigators submit a Data Request Form and a Data Sharing Agreement to the PMG.
2. The PMG reviews submissions for completeness and forwards them to the DAC.
3. The DAC reviews the scientific and ethical integrity of each request and provides feedback using the DAC Feedback Form.

4. Approved requests are listed on the GloBE-Reg website, with annual reports and lay summaries of all ongoing analyses.

5. Where overlap exists between proposed and ongoing projects, applicants are encouraged to collaborate with each other to avoid duplication.

- Timeline and Milestones

Q2 2022 – Ethics approval and beta version of registry platform.
Q4 2022 – Launch of active GloBE-Reg platform.
Q2 2023 – Development of GH module and initial manuscript
Ongoing – Expansion to other therapy modules and long-term data collection.

- Risk Management

- Identified risks include delays in reaching data field consensus, excessive dataset size, and technical implementation challenges. These are mitigated through regular SSG meetings, iterative feedback, and coordinated project management.

- Technical and ethical risks are considered low due to the consortium’s prior experience with similar registry systems.

- References

1. EMA Report: Patient Registries Workshop.
2. EMA Guideline on Registry-Based Studies.
3. Cianfarani S. Safety of Pediatric rhGH Therapy: Front Endocrinol (Lausanne). 2021;12:811846.
4. Miller BS et al. Long-Acting Growth Hormone Preparations. J Clin Endocrinol Metab. 2020;105:e2121-2133.
5. Miller BS, Rosenfeld RG. Monitoring rhGH Safety. Ped Endocrinol Rev. 2018;16(Suppl 1):150-161.